## Sheet1
Week Commencing:
Element |  | 10th May | 17th May | 24th May | 31st May | 7th June | 14th June | 21st June | 28th June | 5th July | 12th July | 19th July | 26th July | 2nd Aug | 9th Aug | 16th Aug | 23rd Aug | 30th Aug | 6th Sept | 13th Sept | 20th Sept | 27th Sept | 4th Oct | 11th Oct | 18th Oct | 25th Oct | 1st Nov | 8th Nov | 15th Nov | 22nd Nov | 29th Nov | 6th Dec | 13th Dec | 20th Dec | 27th Dec | 3rd Jan | 10th Jan | 17th Jan | 24th Jan | 31st Jan | 7th Feb | 14th Feb | 21st Feb
Project planning | Identify possible topics | [21 empty] | 21st Feb: EPQ Submission deadline - 21st February
Project planning | Decide on the initial title
Project planning | Decide on the theme
Project planning | Check for resources
Project planning | Produce a plan
Research | Complete research on what AI is
Research | Complete the research of the history of AI
Research | Complete the research on how the AI is being used
Research | Complete the research on the use of AI in quantum computing
Research | Complete the research on how AI will affect the society | bar: 4th Oct to 1st Nov
Research | Complete the research on the other side of the arguments | bar: 25th Oct to 1st Nov
Primary research | Research how to make a chatbot | bar: 8th Nov to 15th Nov
Primary research | Program a chatbot | bar: 15th Nov
Evaluation | Evaluate the sources used for the project | bar: 20th Dec to 3rd Jan
Production Log | Record the initial ideas
Production Log | Project proposal part A
Production Log | Planning review | bar: 8th Nov
Production Log | Mid-project review | bar: 6th Dec
Production Log | Project product review | bar: 27th Dec to 3rd Jan
Production Log | Presentation record part A | bar: 24th Jan to 31st Jan
Production Log | Summary and reflection | bar: 14th Feb
Work received from the supervisor/ coordinator | The taught skills element | bar: 18th Oct
Work received from the supervisor/ coordinator | Project proposal part B | bar: 4th Oct
Work received from the supervisor/ coordinator | Project proposal part C | bar: 18th Oct
Work received from the supervisor/ coordinator | Presentation record part B | bar: 14th Feb
Essay | Introduction | bar: 4th Oct to 11th Oct
Essay | What is AI | bar: 18th Oct to 25th Oct
Essay | The history of AI | bar: 1st Nov to 8th Nov
Essay | What are the next steps of AI | bar: 8th Nov to 15th Nov
Essay | Is the computer actually thinking | bar: 15th Nov; 6th Dec
Essay | How will AI affect the society | bar: 13th Dec
Essay | Primary research | bar: 13th Dec
Essay | Conclusion | bar: 20th Dec
Essay | Write literature review and bibliography | bar: 20th Dec to 27th Dec
Essay | Improve and check the essay | bar: 20th Dec to 3rd Jan
Presentation | Prepare the presentation | bar: 10th Jan to 7th Feb
Presentation | Presentation week | [21 empty] | 7th Feb: 9th Feb